## Instructions
EPCOR WATER SERVICES (EWS) WASTEWATER CCC-FAC INSPECTION AND APPLICATION CHECKLIST INSTRUCTIONS
Inspection Request Form | Enter project details and provide Consultant confirmation that the Municipal Improvement is ready for inspection. Please ensure all the checklist requirements have been satisfied and that all fields within the form are filled out
CCC-FAC Application Checklist | Provide all required CCC-FAC documentation for the Municipal Improvrment being applied for. Refer to Column B "Location" for where to submit. Refer to Column C "Notes" for additional guidance

## Inspection Request Form
EPCOR WATER SERVICES (EWS) WASTEWATER INSPECTION REQUEST FORM |  |  |  |  | CCC | FALSE
[5 empty] | FAC | FALSE
PROJECT INFORMATION
PROJECT NAME:
MUNICIPAL IMPROVEMENT:
DESCRIPTION (AS LISTED IN CITY OF EDMONTON SERVICING AGREEMENT SCHEDULE ‘D’):
LATEST PROJECT DRAWINGS APPROVED BY CITY OF EDMONTON DEVELOPMENT COORDINATION (INCLUDES RED-LINES) INCLUDED? MUNICIPAL IMPROVEMENT TO BE HIGHLIGHTED |  |  | YES | FALSE | NO | FALSE
INSPECTION ATTENDANCE
WILL YOU (OR A REPRESENTATIVE OF THE DEVELOPER) BE ATTENDING? |  |  | YES | FALSE | NO | FALSE
If yes above, who will be attending?
CCC/FAC INSPECTION REQUEST CHECKLIST
| Yes | No | N/A
Municipal improvement completed as per approved drawings and latest redlines (if applicable) | FALSE | FALSE | FALSE
Pre-Inspection check has been completed per attached requirements | FALSE | FALSE | FALSE
ESC BMPs are installed; maintenance and reporting on-going | FALSE | FALSE | FALSE
All safety concerns have been addressed (Roads are free of debris, snow, ice or any other impediments) | FALSE | FALSE | FALSE
Confrirmation of operational status of the downstream system | FALSE | FALSE | FALSE
All other special provision conditions have been met | FALSE | FALSE | FALSE
RTC system been commisisoned (if applicable) | FALSE | FALSE | FALSE
Have the mains been flushed and MH's/CB's cleaned out? | FALSE | FALSE | FALSE
BY COMPLETING THIS FORM AND REQUESTING AN INSPECTION, YOU ARE VERIFYING THAT THE IMPROVEMENT NAMED ABOVE MEETS ALL THE EPCOR
REQUIREMENTS FOR CCC/FAC. ANY MISREPRESENTATION WILL RESULT IN THE INSPECTION BEING CANCELLED BY THE EPCOR INSPECTOR.
REQUESTED BY:
COMPANY:
Minimum Pre-Inspection Requirements
Reference Material
 A clear plan view drawing highlighting the Municipal Improvement to be inspected. The plan view drawing to be referenced from the approved engineering drawings
 Pre-Inspection photos (confirmation of pre-inspection preparation)
 Consultant reviewed Approved Shop drawings and Details Drawings (if applicable)
Storm and/or Sanitary Sewers, Forcemains (On or Off-Site)
 System is tied in and functional
 Frames and covers on MHs/CBs are in good shape and match drawings
 Grade rings are in good shape with no deficiencies
 Pipe to MH connections have gasketed connections
 Pipe connections are intact/not leaking
 Barrels show no cracks or leaks
 CB and CBMH sumps have been cleaned out
 Manholes are clear any visual debris/blockages
Storm Water Management Facility (SWMF), (Temporary, Interim, or Permanent)
 Confirmation of EWS approved interim inspections for outlets/inlets
 Landscaping and vegetation is complete, from HWL to NWL
 Side slopes have been graded to the approved design
 Water is at NWL (with survey markings as confirmation)
 Boat launch and/or maintenance access is in place and functional
 No obvious erosion or animal damage
 Garbage, construction survey stakes, and other impediments have been removed
 Side slopes are free of grading deficiencies
 Real time control (RTC) system has been commisisoned prior to SWMF CCC inspection (if applicable)
 Control Manhole constructed per approved drawings (horizontal and vertical alignments and all applicable safety protection features)
 Control Manhole davit pull test (stamped report) has been completed (submission to DRENG@epcor.com), if applicable
 ESC measures and best management practices are in place
Swale (Grass or Concrete)
 Confirmation of private site accessibility
 Swales (grass or concrete) are free of obstructions (hardscaping etc.)
 Swale is graded as per approved engineering drawings
 Swale is properly backfilled (concrete only)
 No cracks (concrete) or humps/erosion/dead spots (grass)
 ESC measures and best management practices are in place
 Discharge point of the swale has no obstruction
Ditches and/or Culverts, Ditch Regrading
 Ditches are graded as per approved engineering drawings
 Ditches are sodded or seeded with established growth
 Culverts are undamaged and clear of debris
 Rip rap end treatments are constructed per approved engineering drawings
 ESC measures and best management practices are in place
 Discharge point of the swale has no obstruction
Low Impact Development (LID)
 Verification the facility is functional
 Pipe cleanouts are accessible
 ESC measures and best management practices are in place
Lift Stations/Pump Stations, Real Time Control Structures
 Verification the facility is functional
 Real time control (RTC) system has been commisisoned prior to facility CCC inspection
 Shop drawings
Other Improvements
 Verification that the improvement is constructed as per approved engineering drawings.
 ESC measures and best management practices are in place

## CCC FAC Application Checklist
2026-03-12
EPCOR WATER SERVICES (EWS) WASTEWATER CCC/FAC APPLICATION CHECKLIST
Construction Completion Certificate (CCC)
Description | Location | Notes
No deficiency Inspection Report (EWS Template) | ePlan | Upload copy of EWS provided approved CCC inspection report
No deficiency CCTV Inspection Report (EWS Template) | ePlan | Upload copy of EWS provided approved CCC, CCTV inspection report
CCTV Inspection review media | WinSCP | Ensure Consultant has reviewed the CCC, CCTV inspection reciew package (accuracy, completeness etc.). Submit through EWS WinSCP portal with notification to drainagepd@epcor.com
Leakage testing results (if applicable), (EWS template) | ePlan | Applicable to sanitary mains
Mandrel testing results (if applicable) | ePlan | Applicable to deflected pipe at the discretion of the EWS Inspector
Surface grading verification letter (if applicable) | ePlan | Upload Consultant signed verification letter. Applicable to Municipal improvements with grading components
Registered Easements/URW documentation records (if applicable) | ePlan | All applicable easement/URW/RC documentation pertaining to the specific Municipal Improvement
Operations and Maintenance (O&M) manual (applicable to SWMF, Pump stations, outfalls etc.) submission and EWS Approval confirmation | WinsSCP/ePlan | Ensure Consultant has reviewed the O&M manual submission (accuracy, completeness etc.). Submit through WinSCP portal for EWS review. Upload EWS confirmation email stating O&M Manual approved
AEPA confirmation (applicable to SWMF, Outfalls) | ePlan | Upload AEPA letter stating all environmental approvals are in place
Asbuilt cost form (EWS template) | ePlan | Ensure Consultant has reviewed and confirmed all constructed manholes, pipe sizing, pipe type, catch basins, frame and cover types etc. are accurate to the approved drawings and latest redlines (if any)
Drainage appurtenance form (EWS template) | ePlan | Ensure form is reviwed by Consultant for accuracy and completeness. Form to be completed per as-constructed materials
Geotechnical compliance letter (Letter stating frequency, methods of testing, supported by testing reports) | ePlan | Upload Geotechnical authenticated letter of conformance with supporting compaction testing
Preliminary Asbuilt submission | Consultant Data Loading (CDL) | Upload to EWS CDL Citrix platform, per Vol.03-05 Section 2.0
Preliminary Asbuilt EWS recieved confirmation | ePlan | Upload EWS letter confirming asbuilts "received"
Drainage structure concrete rest reports (if applicable), (EWS template) | ePlan | Applicable for manhole concrete collars, class A bedding, perched manhole cast-in-place base etc. Supported with concrete test results
Water test (if applicable) | ePlan | Applicable for grass swales, concrete swales and ditches. Subject to EWS Inspector request
Final Acceptance Certificate (FAC)
Description | Location | Notes
No deficiency Inspection Report (EWS Template) | ePlan | Upload copy of EWS provided approved FAC inspection report
No deficiency CCTV Inspection Report (EWS Template) | ePlan | Upload copy of EWS provided approved FAC, CCTV inspection report
CCTV Inspection review media | WinSCP | Ensure Consultant has reviewed the FAC, CCTV inspection reciew package (accuracy, completeness, all CCC comments addressed etc.). Submit through EWS WinSCP portal
Mandrel testing results (if applicable), (EWS template) | ePlan | Applicable to deflected pipe at the discretion of the EWS Inspector
Approved Services confirmation from EWS WASS | ePlan | Upload EWS WASS letter confirming services approved
Final Asbuilt submission | Consultant Data Loading (CDL) | Upload to EWS CDL Citrix platform, per Vol.03-05 Section 2.0
Final Asbuilt EWS approved confirmation | ePlan | Upload EWS letter confirming asbuilts "approved"