## Instructions
EPCOR WATER SERVICES (EWS) WATER CCC-FAC INSPECTION AND APPLICATION CHECKLIST INSTRUCTIONS
Inspection Request Form | Enter project details and provide Consultant confirmation that the Municipal Improvement is ready for inspection. Please ensure all the checklist requirements have been satisfied and that all fields within the form are filled out
CCC-FAC Application Checklist | Provide all required CCC-FAC documentation for the Municipal Improvrment being applied for. Refer to Column B "Location" for where to submit. Refer to Column C "Notes" for additional guidance

## Inspection Request Form
EPCOR WATER SERVICES (EWS) WATER INSPECTION REQUEST FORM |  |  |  |  | CCC | FALSE
[5 empty] | FAC | FALSE
PROJECT INFORMATION
PROJECT NAME:
MUNICIPAL IMPROVEMENT:
DESCRIPTION (AS LISTED IN CITY OF EDMONTON SERVICING AGREEMENT SCHEDULE ‘D’):
LATEST PROJECT DRAWINGS APPROVED BY CITY OF EDMONTON DEVELOPMENT COORDINATION (INCLUDES RED-LINES) INCLUDED? MUNICIPAL IMPROVEMENT TO BE HIGHLIGHTED |  |  | YES | FALSE | NO | FALSE
INSPECTION ATTENDANCE
WILL YOU (OR A REPRESENTATIVE OF THE DEVELOPER) BE ATTENDING? |  |  | YES | FALSE | NO | FALSE
If yes above, who will be attending?
CCC INSPECTION REQUEST CHECKLIST
| Yes | No | N/A
Municipal improvement completed as per approved drawings and latest redlines (if applicable) | FALSE | FALSE | FALSE
Pre-Inspection check has been completed per attached requirements | FALSE | FALSE | FALSE
Hydrants are inspected, accessible and operable. Finished flange heights are within Vol.4 standards | FALSE | FALSE | FALSE
All safety concerns have been addressed (Roads are free of debris, snow, ice or any other impediments) | FALSE | FALSE | FALSE
Hydrostatic Pressure Testing results (including hydrants) | FALSE | FALSE | FALSE
Pressure gauge calibration confirmation | FALSE | FALSE | FALSE
Chlorine Residual and Bacteriological Sampling Report | FALSE | FALSE | FALSE
Chlorine meter calibration confirmation | FALSE | FALSE | FALSE
Existing boundary valves are stoppered per the approved drawings | FALSE | FALSE | FALSE
Transfer of Accountability Form (Boundary Valve Stoppers) completed | FALSE | FALSE | FALSE
FAC INSPECTION REQUEST CHECKLIST
| Yes | No | N/A
Municipal improvement completed as per approved drawings and latest redlines (if applicable) | FALSE | FALSE | FALSE
Pre-Inspection check has been completed per attached requirements | FALSE | FALSE | FALSE
Hydrants are inspected and operable. Finished flange heights are within Vol.4 standards | FALSE | FALSE | FALSE
All safety concerns have been addressed (Roads are free of debris, snow or impediments) | FALSE | FALSE | FALSE
All water service CC's are accessible and operable | FALSE | FALSE | FALSE
Existing boundary valves are stoppered per the approved drawings | FALSE | FALSE | FALSE
*Note 1, Taste and Odour sampling will not be scheduled until the above requirements have been met
*Note 2, CCC Inspection/Water commissioning will not proceed until passing Taste and Odour sampling has been confirmed by EWS
BY COMPLETING THIS FORM AND REQUESTING AN INSPECTION YOU ARE VERIFYING THAT THE IMPROVEMENT NAMED ABOVE MEETS ALL THE EPCOR
REQUIREMENTS FOR CCC/FAC. ANY MISREPRESENTATION WILL RESULT IN THE INSPECTION BEING CANCELLED BY THE EPCOR INSPECTOR.
REQUESTED BY:
COMPANY:
Minimum Pre-Inspection Requirements
Reference Material
 A clear plan view drawing highlighting the Municipal Improvement to be inspected. The plan view drawing to be referenced from the approved engineering drawings
 Pre-Inspection photos (confirmation of pre-inspection preparation)
Water Distribution System
 Verification that the improvement is constructed as per approved engineering drawings (all applicable phasing)
 System is functional
 Valves casings are flush with finished grade
 Valves are all operable
 Valve casings have no visual deficiencies and damages
 Grade rings for Manual Air Vents/Flush points are free of deficiencies and damages
 Hydrants are accessible and operable
 Hydrants are painted and numbered
 Flushpoints are accessible and operable
 Valve chambers are free of standing water
 Joint restraint as-constructed photos
 Temporary infrastructure removal photos (if applicable)
 Shop drawings (if applicable)
 All water CC's are accessible and operable
 Transfer of Accountability Form (Boundary Valve Stoppers) completed

## CCC FAC Application Checklist
2026-03-12
EPCOR WATER SERVICES (EWS) WATER CCC/FAC APPLICATION CHECKLIST
Construction Completion Certificate (CCC)
Description | Location | Notes
No deficiency Inspection Report (EWS template) | ePlan | Upload copy of EWS provided approved CCC inspection report
Watermain Flushing Report (EWS template) | ePlan | Ensure Consultant has reviewed flushing report (accuracy, completeness etc.)
Hydrostatic Testing Report (EWS template) | ePlan | Ensure Consultant has reviewed the hydrostatic testing report (accuracy, completeness etc.). Include hydrant testing. Attach pressure gauge calibration confirmation (ensure within validation expiry). Consultant to authenticate this report.
Chlorine Residual and Bacteriological Sampling Report (EWS template) | ePlan | Ensure Consultant has reviewed the chlorine residual and bacteriological testing report (accuracy, completeness etc.). Attach chlorine meter calibration confirmation (ensure within validation expiry). Consultant to authenticate this report.
Taste and Odour Sampling (EWS accepted confirmation) | ePlan | Upload copy of EWS provided approved Taste and odour sampling email
As-Tested Commissioning Plan (if applicable) | ePlan | Applicable to any major changes on the commissioning plan. Refer to the flushing and testing guidelines https://www.epcor.com/content/dam/epcor/documents/supporting-documents/2024-02-27_water_flushing-and-testing-guidelines.pdf
Registered Easements/URW documentation | ePlan | All applicable easement/URW/RC documentation pertaining to the specific Municipal Improvement
Hydrant Flow Test Request (EWS template) | ePlan | Ensure Consultant has reviewed the hydrant flow test request report (accuracy, completeness etc.)
Thrust Block Report and Concrete Test Results (EWS template) | ePlan | Ensure Consultant has reviewed the thrust block and concrete testing report (accuracy, completeness, photo submission etc.). Attach concrete testing support. Consultant to authenticate this report.
Asbuilt Quantities and Cost Report (EWS template) | ePlan | Ensure Consultant has reviewed and confirmed all constructed pipe sizing, pipe type, valves, hydrants and all other water appurtenances are accurate to the approved drawings and latest redlines (if any). Ensure rebateable items are identified in either the WMCS Sheet B or PDTM Sheet C with supporting documentation
Joint Restraint As-constructed Photos | ePlan | Upload to "Documents" folder in ePlan
Temporary infrastructure removal Photos (if applicable) | ePlan | Upload to "Documents" folder in ePlan. Applicable to projects where it's unknown when the future phase tie in will commence
Preliminary Asbuilt submission | email/ePlan | Submit PDF and DGN files to Wtraprvd@epcor.com per Vol.04 Section 1.4. Upload EWS Inspector email confirmation of "received" to ePlan application
Final Acceptance Certificate (FAC)
Description | Location | Notes
No deficiency Inspection Report (EWS template) | ePlan | Upload copy of EWS provided approved FAC inspection report
Approved Services confirmation from EWS WASS | ePlan | Upload EWS WASS letter confirming services approved
Final Asbuilt submission | email/ePlan | Submit PDF and DGN files to Wtraprvd@epcor.com per Vol.04 Section 1.4. Upload EWS Inspector email confirmation of "reviewed" to ePlan application